## EE progress
IMPLEMENTATION OF KEY EED/EPBD ARTICLES | [6 empty] | IR 2018 Relevant EE imlementation indicators in % (Status - October 2018)
CONTRACTING PARTY: MACEDONIA |  | Current Status (no activities/ongoing/partly or fully transposed/implemented) | Progress between Nov 2018 and March 2019 (YES/NO) | Comments on achieved progress and main challenges (Nov. 2018- March 2019) | TA available/required | Planed activities (March-June 2019) | AL | BiH | GE | K* | MK | MD | MN | SR | UA
EED - NEEAPs and Targets | EED NEEAP preparation and MVP reporting (Art 24) | ONGOING ACTIVITIES | YES | GIZ expressed interest for TA | TA AVAILABLE | Preparation and adoption of the NEEAP, MVP Legal basis with adoption of the EE Law, Training s for MVP by GIZ, MVP Rulebook to be prepared by GIZ. | 62% | 63% | 24% | 67% | 70% | 85% | 77% | 75% | 69%
| 2020 EE Target (Art 3) and Annual EED Reports (Art 24) | ONGOING ACTIVITIES | YES | GIZ expressed interest for TA, ME has skills for preparation of EED Reports | TA AVAILABLE | Preparing and adoption of the NEEAP, Preparation of EED Report by ME.
| EEO schemes: calculation of target and notification to ECS (Art 7) | ONGOING ACTIVITIES | YES | Public consultation of the new EE Law, | TA NEEDED | After the adoption of New EE law there will be preparation of analysis for most suitable EEO scheme model, secondary legislation preparation TA EBRD ???
| Public Sector Obligations: Inventory of Central Government Buildings; 1% Target or alternative maeasures/ notification to ECS (Art 5); EE Procurement (Rulebook) (Art 6) | ONGOING ACTIVITIES | YES | Public consultation of the new EE Law, Phase 1 – Inception / Scoping for inventory TA CONNECTA | TA NEEDED | After the adoption of New EE law there will be preparation of secondary legislation , CONNECTA final inception report for inventory establishing &target/notification, EE procurement Ruelebook preparation TA needed.
EED - ESCO Market Development and Financing | Legal framework adoption, model contract(s) prepared and available (Art 18), projects ongoing | ONGOING ACTIVITIES | YES | Public consultation of the new EE Law, | TA AVAILABLE | Legal basis in the new EE Law, ESCO Agreement legal gap analysis TA EBRD , TA EBRD available for the local Government for preparing tendering documentation for ESCO Projects | 40% | 53% | 30% | 43% | 28% | 51% | 53% | 75% | 78%
| Improve/ facilitate the establishment of new financing facilities; EE Funds (Revolving?) (Art 20) | ONGOING ACTIVITIES | NO PROGRESS | World Bank express interest for loan | TA NEEDED | World Bank loan for establishing EE Fund 20-30milEUR, MF to be consulted for financing models about this Project Proposal
EPBD/EED - EE in buildings | EP Calculation Methodology (Art 3) ; Setting of MEPs (Art 4); Calculation of Cost-Optimal Levels (Art 5) | PARTLY TRANSPOSED / IMPLEMENTED | NO PROGRESS | Public consultation of the new EE Law, | TA NEEDED | After the adoption of New EE law there will be preparation of secondary legislation,TA EBRD ??? | 30% | 59% | 28% | 39% | 40% | 54% | 74% | 67% | 56%
| Adopted/implemented regulation and EP certification ongoing (Art 11); Registry (Art 12) | PARTLY TRANSPOSED / IMPLEMENTED | NO PROGRESS | Public consultation of the new EE Law, | TA NEEDED | After the adoption of New EE law there will be preparation of secondary legislation, TA EBRD ???
| Renovation Strategy (EED, Art 4) | ONGOING ACTIVITIES | NO PROGRESS | Public consultation of the new EE Law, CONNECTA didn’t express interest for preparation of Typology, GIZ and HABITAT expressed readiness to participate in this Project | TA NEEDED | After the adoption of New EE law there will be adoption of secondary legislation, TA needed for closing financial construction for preparation of the Typology and Strategy
Strengtening of institutional capacities | Ministries - EE Departments; Implementing agencies (if exist); Local/regional level; Oth. enforcement bodies (inspectorates, surveillance bodies) | ONGOING ACTIVITIES | YES | Functional analysis of the energy sector was conducted, from which arise the necessarity of organizational change of the departments in the Energy Sector and to increasing the number of employees, taking into account the trend of the European energy policy and the obligations that Macedonia took over by ratifying the Agreement on Establishment of the Energy Community and taking into account the enlargement of the scope of the Agreement related to the bonding of the energy and climate policies | TA NOT NEEDED | Ongoing process for employment of 5 persons in the Energy Sector of the Ministry of Economy, TA USAID for preparation of secondary legislation of Energy Consumption Labeling and Eco Design and capacity building of market inspectorate | 54% | 48% | 33% | 65% | 40% | 75% | 75% | 75% | 74%
NO ACTIVITIES
ONGOING ACTIVITIES
PARTLY TRANSPOSED / IMPLEMENTED
FULLY TRANSPOSED, PARTLY IMPLEMENTED
FULLY TRANSPOSED AND IMPLEMENTED
YES
NO PROGRESS
TA AVAILABLE
TA NEEDED
TA NOT NEEDED